## Slide 1
NORTHEAST BEACHES 2013
State Boat Channel Emergency Dredging & Beach Fill at Robert Moses State Park
Presented to:
Northeast Shore & Beach Preservation Association
September 10, 2013

## Slide 2
Permits
NYS DEC, USACE
NYS Parks – OGS
Owner Administration
GPI, Parks Ecological, LLC
Plover Monitoring
Prime Consultant
Parsons Brinkerhoff
Engineering, CM
Gahagan & Bryant
Truck Haul & Grading
Grace Industries, LLC
NYS DOT
Democrat Pt. Stockpile - Truck Haul
Tri-Venture (Bove/Tully/Picone)
Robert Moses Emergency Beach Fill
Hyd. Dredging
Fire Island Inlet
Norfolk Dredging
Hyd. Dredging
Boat Channel
Village Dock, Inc.

## Slide 3: INTRODUCTION
Super Storm Sandy 10-29-12 Damage
  Robert Moses Beaches (5 miles), Boardwalk
  New York State Boat Channel (shoaling)
Project Locations
The Pre-Construction Process
Emergency Beach Fill Contracts
  Owner - NYS Parks, administered by Office of General Services
    Village Dock, Inc. – Hydraulic Dredge
    Grace Industries, LLC – Truck Haul, Grading Plover Habitat
  Other - NYS DOT – Norfolk Dredge - Tri-Venture–Truck Haul
GOAL: Beaches Restored by Memorial Day 2013
Notes: 3.5 million visitors annually at R.M.

## Slide 4: CBS Channel 2 NEWS VIDEO CLIP

## Slide 5: Boardwalk Damage
Sand eroded away
8 Feet Vertically
Notes: Millions of CY over about 5 miles - These contracts about xxx cy over about 1 mile

## Slide 6
Brooklyn
Long Beach
Project Area
Queens
Manhattan
Bronx
East Northport
Port Washington
Garden City
Deer Park
VICINITY MAP

## Slide 7
PROJECT AREA
Fire Island Inlet
Democrat Point
Ocean Parkway
Captree State Park
Field # 4
Field # 5
Robert Moses State Park

## Slide 8
State Boat Channel Emergency Dredging
Contractor: Village Dock With Hydraulic Dredge
Dredge Pipeline
Emergency Beach Fill
PROJECT LOCATIONS
Notes: Native Beach Fill sand – 0.5 mm medium on the fine side,
Channel sand – 0.4 mm fine sand on the medium side.

## Slide 9
Grace - Trucking Borrow Area
Norfolk Dredging Stockpile –
Tri-Venture Trucking
Fire Island Inlet
Democrat Point
PROJECT LOCATIONS

## Slide 10
Grace - Trucking Borrow Area
Norfolk Dredging Stockpile
Field #4
Field #5
PROJECT LOCATIONS

## Slide 11: TYPICAL PRE-CONSTRUCTION PROCESS
New Permits – NYS DEC, USACE NY District
  Planning, sampling, testing, studies, documentation.
  Joint Permit, NEPA, Water Quality Cert., Plover windows
Existing Permit Modifications and Approvals
  Channel dredging depths and widths
  Beach fill locations and geometries
  Ingress and egress points to beach & borrow
Planning, design, PSE, Procurement, Bid, Award
Funding

## Slide 12: TYPICAL vs. EMERGENCY PROCESS
4 Months Procure
12
6 Months Design
2 Months Planning, Design, Permits
2 weeks Procurement
14 months Planning and Permitting
Typical Beach Dredging Project Process (2 years +)
Emergency Process (2.5 months)
Jan | Mar | May | July | Sep | Nov | Jan | Mar | May | July | Sep | Nov
2013
2014

## Slide 13
Permits
NYS DEC, USACE
NYS Parks – OGS
Owner Administration
GPI, Parks Ecological, LLC
Plover Monitoring
Prime Consultant
Parsons Brinkerhoff
Engineering, CM
Gahagan & Bryant
Truck Haul & Grading
Grace Industries, LLC
NYS DOT
Democrat Pt. Stockpile - Truck Haul
Tri-Venture (Bove/Tully/Picone)
Robert Moses Emergency Beach Fill
Hyd. Dredging
Fire Island Inlet
Norfolk Dredging
Hyd. Dredging
Boat Channel
Village Dock, Inc.

## Slide 14: BOAT CHANNEL DREDGING
Planning and Design – Jan and Feb 2013
Solicitation Dates - Feb 16 - Feb 19, 2013
Pre Bid Conference Call - Feb 18
Bid Date Feb 19, 2013
Notice to Proceed Feb 20, 2013
Start Dredging March 5, 2013
Finish Dredging May 15 (Beach) - June 6, 2013
Stock Pile at Berm
Memorial Day May 27

## Slide 15: BOAT CHANNEL DREDGING
Village Dock, hydraulic dredge - Scrod II – 16 inch
  Dredge 1100hp, booster pump 800hp
  8,000 ft. channel, 160 ft./day, 4260 cy/day, 385,000 cy
  Pipeline length 7,000 to 12,500 ft.
  Placement at Fields 4 & 5
  Engineering During Construction
    Quantities and channel depths/widths modified
    Permit modifications
    Multiple re-designs
    Inspection, Hydrographic Surveys, Measurement & Payment

## Slide 16
Excerpts from Weekly Reports

## Slide 17
Excerpts from Weekly Reports

## Slide 18: BOAT CHANNEL DREDGING 16 inch Hydraulic Dredge Scrod II

## Slide 19: BOAT CHANNEL DREDGING

## Slide 20: BOAT CHANNEL DREDGING

## Slide 21: BOAT CHANNEL DREDGING

## Slide 22: GRACE-TRUCKING FROM DEMOCRAT PT.
Planning and Design – Jan and Feb 2013
Solicitation Date March 12, 2013
Bid Date March 13, 2013
Notice to Proceed March 13, 2013
Start Truck Haul March 21, 2013
Finish Truck Haul April 12, 2013
Plover Habitat Grading - June 7 thru June 14

## Slide 23
Ten Trucks, 30 – 40 ton. About 7,100 truck hauls
Haul from Democrat Pt. approximately 238,000 cy
Haul days approximately 18, 13,200 cy/day
Placement at Field 4 & 5
Engineering During Construction
  Quantities and sand borrow locations modified
  Permit modifications
  Surveys, Measurement and Payment
GRACE - TRUCKING FROM DEMOCRAT PT.
Notes: Verbally mention borrow areas permitted – existing elevation about +15?? Down to elevation +3 what datum. Borrow location added because funding and schedule allowed for it.

## Slide 24
GRACE TRUCKING FROM DEMOCRAT PT.
Notes: Verbally mention borrow areas permitted – existing elevation about +15?? Down to elevation +3 what datum. Borrow location added because funding and schedule allowed for it.

## Slide 25
GRACE TRUCKING FROM DEMOCRAT PT.

## Slide 26
GRACE TRUCKING TO ROBERT MOSES

## Slide 27
GRACE TRUCKING TO ROBERT MOSES

## Slide 28
Plover Grading Area
GRACE PLOVER GRADING

## Slide 29
GRACE - PLOVER GRADING

## Slide 30
GRACE PIPING PLOVER GRADING
Looking NW

## Slide 31: NYS DOT - Norfolk Dredging & Stockpile
24” Hydraulic Dredge Charleston – 10,000 HP
Dredged F.I. Inlet – Stockpile 200,000 cy ++
Tri-Venture Trucking from Democrat Pt.
Haul days approximately 30
Placement at Field 5
Coordination – State Agencies, Engineers and Contractors.

## Slide 32: NYS DOT - Norfolk Dredging & Stockpile 24 in. Hyd Dredge “Charleston”

## Slide 33: NYS DOT - Norfolk Dredging & Stockpile

## Slide 34: Emergency Beach Fill – Summary
Grace Borrow Area
Norfolk Dredging Stockpile
Field #4
Field #5
Tri-Venture
Grace Industries
Village Dock
Legend
385,000 CY
238,000 CY
150,000 CY
7800 ft. of Beach - Restored

## Slide 35: Robert Moses Emergency Beach Fill Summary with Cost / Cy
Contractor | Borrow Source | Quantity Cy. | Cost $/CY
Village Dock | Boat Channel | 385,000 | $18
Grace Industries | Democrat Pt. | 238,000 | $8
Tri - Venture | Democrat Pt. | 150,000 | Not Available
TOTAL |  | 773,000 | 
Notes: Third option for Harbor material will give us capacity for 20 years.
Source of slide: Frank Hamons’ presentation to DMMP Executive Committee, 10/26/11.

## Slide 36: Robert Moses Emergency Beach Fill Summary
 | March | April | May | June | July
Village Dock
Grace Industries
NYS DOT - Tri-Venture
Dredging Complete June 6th
Dredging Start
March 5th
Mem. Day Holiday Shutdown
Trucking Start
March 21st
Grading Beach and Plover Habitat
Complete June 14th
Trucking Start
April 13th
Trucking Complete
May 12th
Trucking Finish
April 12th
238 k-cy – 13,600 cy/day
385 k-cy – 4,260 cy/day
150 k-cy – 13,600 cy/day
Notes: Third option for Harbor material will give us capacity for 20 years.
Source of slide: Frank Hamons’ presentation to DMMP Executive Committee, 10/26/11.

## Slide 37: Questions ????

## Slide 38: End
38

## Slide 39
39
Notes: Native beach sand – Grain Size Distribution

## Slide 40: State Boat Channel Emergency Dredging
40
Field Area #4
Field Area #5
State Boat Channel Emergency Dredging
Contractor: Village Dock With Hydraulic Dredge
Dredge Pipeline
Emergency Beach Fill

## Slide 41
Grace Trucking Borrow Area
Norfolk Dredging Stockpile –
Tri-Venture Trucking
Fire Island Inlet
Democrat Point
PROJECT LOCATIONS

## Slide 42
Grace Trucking Borrow Area
Norfolk Dredging Stockpile
Field Area #4
Field Area #5
PROJECT LOCATIONS