## Slide 1: Extreme Weather Pumping & Dewatering
WEDA Midwest Chapter Spring 2012 Meeting
April 26, 2012
Presented by Scott Ponstein

## Slide 2: Project Overview
Preferred Sands silica sand mine
Woodbury, MN
January 2012
Sand silica waste, by-product of silica sand washing process
Pump sand waste from frozen settling pond
Dewater in geotextile tubes

## Slide 3: Preferred Sands

## Slide 4: Scope of Work
Very short time frame (3 days from approval to mobilization)
Remove 2 million gallons of material from frozen settling pond
Utilize Pit Hog pumps to move material
Geotextile tubes to dewater

## Slide 5: Equipment
Chain saw
Gantry crane & truck-mounted boom crane
(2) Pit Hog pumps with hydraulic power packs
(2) 6” diameter HDPE pipelines
22 gph polymer makedown & injection system
(2) Geotextile tubes, 75’ by 200’
10,000 lb off road forklift
Miscellaneous torches and heaters.

## Slide 6: Method
Holes cut in ice using chain saw
Pumps, suspended by cranes, lowered down into pond
Pumped sand slurry injected with polymer
Sand slurry-polymer mixture pumped into geotextile tube for dewatering
Geotextile tube weep water pumped back to pond

## Slide 7: Site Photos
Hole cut in ice

## Slide 8: Site Photos
Pump suspended with crane truck

## Slide 9: Site Photos
Pumping operation

## Slide 10: Site Photos
Polymer system hut with crane truck & pond in background

## Slide 11: Site Photos
Geotextile tube prior to filling

## Slide 12: Site Photos
Geotextile tube during pumping

## Slide 13: Site Photos
Weep water drainage

## Slide 14: Site Photos
Weep water return pipeline

## Slide 15: Challenges
Below zero temps nearly every day
Working on ice (slips/falls, breaking through)
Keeping ice from forming around the pumps
Polymer system freezing up
Pipelines freezing during shutdowns
Geotextile tube freezing overnight

## Slide 16: Complications of the Cold
Actual polymer dose was up to 4 times what was expected
Had to disassemble pipelines and completely drain them every night to prevent freezing
Stress on mechanical equipment (pumps)
Geotextile tubes performed differently
3-4” ice formed on geotextile tubes overnight; hard to dewater in the morning

## Slide 17: Summary
Level of the pond lowered 3 ft
Depth of sand waste lowered 5 ft
Project completed in 14 days (including mobilization & demobilization)
Satisfied client

## Slide 18: Questions about the project?

## Slide 19: Contact Information
Scott Ponstein, Field Engineer
sponstein@infralt.com
Infrastructure Alternatives
  7888 Childsdale Ave NE
  Rockford, MI 49341
  616-866-1600
  www.InfrastructureAlternatives.com